## Slide 1: Presentation to the GAC: A preliminary presentation of the Capacity Building program evaluation
25 June 2018, ICANN 62, Panama
Alice Munyua

## Slide 2: Agenda
Introduction
Overview of program
Evaluation Methodology
Some preliminary observations
Summary and Way Forward
Discussion
Notes: This slide can be used for text, graphics or any other elements.

## Slide 3: Overview of program
Section 1

## Slide 4: Overview of Program
Concept proposed through work plan from USRWG 2016
  Workplan endorsed by the GAC
Demand driven capacity building
  Agendas and locations determined by the GAC
  Locations chosen to provide diversity of access and leverage existing events
Pre and post workshop surveys
  Contents determined by target audience
  Outcomes evaluated after each event
Notes: This slide can be used for text, graphics or any other elements.

## Slide 5: Overview of Program, P2
Eight workshops delivered
  Since 2017 there have been 8 workshops in 5 regions
    Africa
      Nairobi, Kenya; Johannesburg, South Africa and Dakar, Senegal
    Asia/Pacific
      Nandi, Fiji; Kathmandu, Nepal
    Middle East
      Abu Dhabi, UAE
    Latin America – Caribbean
        San Juan, Puerto Rico; Panama
  Over 200 participants from GAC, Law Enforcement Agencies and non GAC member countries
  Multistakeholder participation and presenters

## Slide 6: Overview of Program, P 3
Some common themes:
  Internet Ecosystem
  Operation of ICANN and Role of the GAC
  PDPs
  Operation of the DNS
  Personal data Protection & Access to WHOIS data
  Security and stability
Some location specific programs
  Disaster preparedness, resilience and recovery

## Slide 7: Evaluation Methodology
Section 2

## Slide 8: Evaluation Methodology
Evaluation methodology presented to USRWG
  Methodology endorsed by the GAC
Multi modal evaluation
  Data gathered through multiple sources:
    GAC wide online surveys were conducted at the beginning of the project and repeated towards the end
    Pre and post workshop on-line surveys were conducted for the regional and some thematic workshops;
    face to face meetings using focus groups and one on one interviews were conducted at some ICANN meetings
    Three evaluation clusters were used
      Process approach
      Implementation of the project
      Efficacy and sustainability of capacity development activities

## Slide 9: Evaluation Methodology
Evaluation methodology and framework presented to USRWG
  Methodology endorsed by the GAC
  Evaluation report currently includes responses from 6 surveys
  Focus group discussions from 4 workshops
Analysis of workshop specific results and feedback from participants
Aggregate outcomes analysis (examine using criteria of relevance, efficiency, effectiveness and sustainability)
Observations on content
Observations on Methodology
Notes: Multiple sources of data: online surveys, focus group discussions and analysis of documentation, GAC wide surveys
Documents generated along the lifespan of this first phase. GAC communiqués, related more to the design of the project and less to outputs and activities conducted, while others related to process. Studying these documents helped in formulating a picture of how the project was conducted. Communiques: Marrakech (March 2016), Hyderabad (November 2016) and Copenhagen (March 2017).

## Slide 10: Some Preliminary Observations and Recommendations
Section 3

## Slide 11: Some Preliminary Observations, P.1
High levels of satisfaction –
  Ratings for workshops averaged 4.5 out of 5
Requests for online materials and materials for varying levels of experience –
  Participants valued availability of materials in advance of workshops and requested an online learning platform for GAC members that could also be integrated into orientation
While the project is specifically target for government participants, respondents found the multistakeholder approach valuable and appreciated presentations and participation by non-governmental stakeholders

## Slide 12: Some Preliminary Observations, P.2
Opportunities
-Online learning platform for GAC and governments. ICANN Learn
-GAC members to host regional meetings in preparation for ICANN meetings?
-Explore the value add beyond the ICANN community?
Concerns
-Significant change at the impact level (political, economic, legislative, cultural, and social spheres)
-High turn-over.
-Difficult to keep track of benefits to the under-served countries in the longer term.
-Budget

## Slide 13: Some Preliminary Observations, P3
Preliminary Recommendations
Creation of online learning platform for GAC members and those who might not have joined the GAC yet.
  Materials on process and roles
  Materials on current policy issues
Evolution of the Capacity Building workshop program into a regularly budgeted area of activity – perhaps linked to the onboarding process for new GAC members
Maintain the demand driven model for future capacity building activities
Notes: Survey data can be used to develop relevant content for the on-line materials

## Slide 14: Summary and Way Forward
Section 3

## Slide 15: Summary and Way forward
Next steps
Integration of most recent workshop reports and evaluations
Post survey results gathered on Panama Workshop
  Survey will launch by end of ICANN 62 and close within 2 weeks
  Encourage all participants to return evaluations
  Revisions made to evaluation report to incorporate last survey and update observations
  Final evaluation circulated to the GAC by the end of July 2018
  Presentation of report ICANN 63 Barcelona October 2018
Discussion
Notes: Just a sample among many IG conferences and processes in the next 6 months

## Slide 16: Discussions
Thank you and discussions